## Gantt Chart
PROJECT GANTT CHART - PAWCARE MOBILE-BASED PET HEALTH MANAGEMENT SYSTEM
Current status: Proposal completed ¦ Development not started |  |  |  |  | 13-WEEK PROJECT TIMELINE
Task ID | Task / Subtask | Status | Start Week | Duration (Weeks) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
A | PROPOSAL PREPARATION
A1 | Research and problem definition | Completed | 1 | 1 | bar: 13-WEEK PROJECT TIMELINE 1
A2 | Project objectives and scope | Completed | 1 | 2 | bar: 13-WEEK PROJECT TIMELINE 1 to 13-WEEK PROJECT TIMELINE 2
A3 | Literature review and methodology | Completed | 2 | 2 | bar: 13-WEEK PROJECT TIMELINE 2 to 13-WEEK PROJECT TIMELINE 3
A4 | Proposal editing and formatting | Completed | 3 | 1 | bar: 13-WEEK PROJECT TIMELINE 3
A0 | Proposal completed milestone | Completed | 3 | 0 | bar: 13-WEEK PROJECT TIMELINE 3
B | SYSTEM DESIGN & DEVELOPMENT
B1 | System requirements, diagrams and wireframes | Not Started | 4 | 1 | bar: 13-WEEK PROJECT TIMELINE 4
B2 | Development environment and project setup | Not Started | 4 | 1 | bar: 13-WEEK PROJECT TIMELINE 4
B3 | Laravel authentication and pet-profile API | Not Started | 5 | 1 | bar: 13-WEEK PROJECT TIMELINE 5
B4 | Vaccination, health and appointment modules | Not Started | 6 | 1 | bar: 13-WEEK PROJECT TIMELINE 6
B5 | Android login, registration and navigation | Not Started | 7 | 1 | bar: 13-WEEK PROJECT TIMELINE 7
B6 | Android CRUD and API integration | Not Started | 8 | 2 | bar: 13-WEEK PROJECT TIMELINE 8 to 13-WEEK PROJECT TIMELINE 9
B7 | Reminder, dashboard and system enhancement | Not Started | 10 | 1 | bar: 13-WEEK PROJECT TIMELINE 10
B0 | Development milestone | Not Started | 10 | 0 | bar: 13-WEEK PROJECT TIMELINE 10
C | TESTING, DOCUMENTATION & FINALISATION
C1 | System and API testing with bug fixing | Not Started | 11 | 1 | bar: 13-WEEK PROJECT TIMELINE 11
C2 | User acceptance testing and improvements | Not Started | 11 | 1 | bar: 13-WEEK PROJECT TIMELINE 11
C3 | Report writing, diagrams and screenshots | Not Started | 12 | 1 | bar: 13-WEEK PROJECT TIMELINE 12
C4 | Final testing and repository cleanup | Not Started | 13 | 1 | bar: 13-WEEK PROJECT TIMELINE 13
C5 | Presentation slides, rehearsal and backup | Not Started | 13 | 1 | bar: 13-WEEK PROJECT TIMELINE 13
C0 | Final project milestone | Not Started | 13 | 0 | bar: 13-WEEK PROJECT TIMELINE 13

## Legend
LEGEND
Completed proposal activities
Planned system design and development
Planned testing, documentation and finalisation
◆ | Milestone - end of phase
Phase header row
Not Started status